## Project Planner
Project Planner - Bradley Jackson
Select a period to highlight to the right. A legend describing the chart follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Duration |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS (Weeks Starting Mon 20th Jan)
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 21 | 22 | 23 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
D3 - Animated Delivery of Data | 1 | 3 | 1
D3 - Histogram of User Polarity | 1 | 3 | 1
D3 - Visualisation of Neighbours | 3 | 1
Database - Delete User Data if Requested | 1 | 1 | 1
Database - 24 Hour Private Mode | 1 | 1 | 1
Firefox - Port Latest to Extension | 2 | 2
Experiment 1 - A method to upload a .json history file directly | 2 | 1
Extension - Resolve all remaining misc errors | 1 | 3 | 1
Experiment 1 - Source Participants | 3 | 2
Experiment 1 - Collect Data | 5 | 4
Analysis - Compile Z-Score Classification based on Exp. 1 | 7 | 2
Experiment 2 - Advertise & Seek Participants Locally | 9 | 3
Experiment 2 - Prepare Questionnaire | 9 | 3
Experiment 2 - Collect Data | 13 | 6
Lit Review | 6 | 8
Draft Poster/Ad for Participants (Exp. 2) | 2 | 3
Thesis - Lit Review | 4 | 8
Thesis - Data Analysis & Discussion | 11 | 13
Thesis Writing | 11 | 13
Dissertation Prep | 23 | 4
Full Project | 1 | 27 | 1
Activity 14
Activity 15
Activity 16
Activity 17
Activity 18
Activity 19
Activity 20
Activity 21
Activity 22
Activity 23
Activity 24
Activity 25
Activity 26